TERM OF REFERENCE (TOR) FOR ENTOMOLOGY CONSULTANT UNDER THE PROJECT: EFFECTIVE SURVEILLANCE FOR MALARIA OUTBREAK DETECTION IN PERI-URBAN AREAS OF MOZAMBIQUE

| Organization: | Malaria Consortium |
| --- | --- |
| Title: | Formative Assessment Entomology Consultancy to improve entomological surveillance, data flow and integration for malaria outbreak prevention and early detection and provide intensive training |
| Project: | Effective Surveillance for Malaria Outbreak Detection in Peri-urban Areas of Mozambique |
| Place of Work: | On-site: Malaria Consortium offices and Ministry of Health – National Malaria Control Program |
| Output Technical Lead | Dr Sónia Maria Enosse |
| Duration: | 69 working days from August 2026 to March 2027 |
| Fee: | Applicable organizational rates |

ORGANISATIONAL HISTORY

Founded in 2003, Malaria Consortium is one of the world's leading non-profit organizations dedicated to the comprehensive control of malaria and other communicable diseases and child health in Africa and Southeast Asia. Malaria Consortium works with communities, government and non-government agencies, academic institutions, and local and international organizations, to ensure good evidence supports delivery of effective services, providing technical support for monitoring and evaluation of programmes and activities for evidence based decision-making and strategic planning. The organization works to improve not only the health of the individual, but also the capacity of national health systems, which helps relieve poverty and support improved economic prosperity.

PROJECT CONTEXT

Mozambique is among the countries with the highest malaria burden, and transmission is heterogeneous across the country. While Maputo City is among the low transmission areas, (0% parasite prevalence reported in the 2022–23 DHS, compared to the national prevalence of 32%). Malaria cases in Maputo City increased substantially in the first quarter of 2025 compared to the same period in 2024. The malaria hospitalization rate also increased in 2025 compared to 2024, while the case fatality rate remained stable-. Of the city’s seven municipal districts ranging from urban to rural in classification, the largest surges were in peri-urban districts such as KaMavota, KaMubukwana and KaMaxakeni.

Malaria Consortium in coordination with NMCP and the province is implementing the Effective Surveillance for Malaria Outbreak Detection in Peri-urban areas of Mozambique project. The project aims to implement interventions to strengthen early detection and effective capacity to plan response to malaria outbreaks in peri-urban areas, addressing the surveillance gap revealed by an early undetected outbreak of malaria cases in Maputo city.

ENTOMOLOGICAL ASSESSMENT AND BUILD CAPACITY CONTEXT OBJECTIVES

The entomological surveillance component is the cornerstone of malaria control, generating high-resolution, routinely updated evidence that guides operational and strategic decisions across diverse transmission settings by systematically measuring indicators such as vector species composition, density, biting behaviour, sporozoite rates, entomological inoculation rate (EIR), and insecticide resistance profiles; these data enable precise spatial and temporal targeting of vector control interventions.

Mozambique has made notable progress in strengthening this system, improving data availability for decision-making. However, key challenges persist, including gaps in data digitalization - which still relies on physical reports, insufficient use and integration of entomological surveillance outputs into routine programmatic responses to identify potential outbreaks, all of which constrain the full operationalization of evidence-based, adaptive malaria control, especially in low transmission areas.

The Comprehensive Assessment (CA) aims to understand how the entomology surveillance system is working through mapping the key interventions, report system and data flow, data use and its integration with other key components off malaria program. This will include assessment of available tools, staff and its technical capacity to successfully drive entomological interventions, and finally deliver intensive training on vector surveillance, control and data systems.

OBJECTIVES OF THE CONSULTANCY

To structure and carry out a CA guided by the scope of work to be aligned with the determined components, to identify entomological system gaps, bottlenecks and inefficiencies, and generate a technical report with practical recommendations for NMCP to strengthen entomological surveillance and its integration with epidemiological monitoring. Specific objectives are:

Objective 1. To structure and carry out a comprehensive assessment (CA)

Specific objectives

- Assess existing entomological surveillance systems and practices

Objective 2. To adapt, revise and develop tools for entomological procedures for outbreak detection

Specific objectives

- Develop an integrated epidemiological–entomological surveillance framework for outbreak prevention

- Revise or develop essential tools to strengthen the entomological surveillance system

Objective 3. Build capacity of MISAU staff on entomology surveillance interventions for outbreak and all tools and approaches developed

Specific objectives

- Deliver intensive training on vector surveillance, control and data systems

SCOPE OF WORK

The consultancy work will be conducted at national level within the Ministry of Health through the National Malaria Control Programme (NMCP), the Department of Health Surveillance (DHS), the Department of Health Information (DIS), and the Health Services (Malaria) unit at the Maputo City Municipality, districts and health facilities (HF). When needed the consultancy will include contacting partners working or supporting malaria entomological interventions and health information systems.

These include field visits to selected HF and district officers, as well as interviews with central-level malaria program, surveillance department, entomology and information system units. While the work will include national level data and information, the field work and detailed evaluation will be based in 3 Maputo City municipal districts (KaMavota, KaMubukwana and Katembe, including key personnel from these districts, the municipal health services (malaria area), the Ministry of Health, and partners. The Consultancy will comprise three key phases described below.

Phase 1. Develop a Comprehensive Assessment (CA) framework, design tolls for data collection, analysis and write technical report

- Tools and approach for CA. Design a detailed CA framework and all necessary tools for data collection, including data base to store information.

- Entomological interventions. Assess the entomological interventions in Maputo city, frequency implementation, coverage and distribution of sentinel sites.

- Entomological data. Assess the indicators collected and reported, data flow, periodicity, system used, how data is processed, analysed, shared, and used for programme management decision-making.

- Tools and protocols (Manuals, SOPs, guidelines). Mapping existing tools (type and up to date) in all CA entomological components, and explore the gaps availability and use of response protocols

- Stakeholders capacity at central, provincial and district levels (people and knowledge available). Staffing (are enough people available at different levels to perform effective entomological functions), knowledge, training and capacity existing and gaps to manage their work, role and responsibilities; training: type and frequency, and provided by whom, including in malaria case management at health facilities; understanding of budgetary requirements and availability of adequate funding.

- Data use. How data are used at different levels, existing tolls to guide utilizations at different levels, kind of evidence to measure data use; If data is used in an integrated approach (epidemiological, entomological and climate) in what frequency. How data is used to early detect or prevent outbreaks of malaria.

- Communication and coordination mechanisms. Existing of coordination and communication mechanism at different stakeholders (central, provincial, district and HF), periodicity, kind of coordination platforms existing, evidence existing.

- Climate Data. Assess the variable climate data to use with entomological component to monitor malaria trends and vectors control: how data are collected and periodicity; system used to collect and integrated with other data elements.

- Outbreaks detections, plan and response. Approaches or system used to prevent, or for early detection of malaria outbreaks, capacity to plan and respond, kind of intervention implemented in Maputo city and approaches used to monitor in line with epidemiological data.

- CA data Analysis. Analyse the data collected across qualitative and quantitative dimensions, in accordance with the procedures and protocols specific to each component.

- Write the CA report. Identify entomological system gaps, bottlenecks and inefficiencies, SOP and approaches for outbreak detection and generate a technical report with practical recommendations to strengthen entomological surveillance and its integration with epidemiological monitoring. Conduct a cross-analysis of epidemiological variables collected by the consultancy, in order to establish a comprehensive picture of the entomology for epidemiological malaria trends.

Deliverables:

- Inception report with the plan for Comprehensive Assessment (CA) and related tolls designed and approved

- Formative assessment data base with all information collected

- Narrative and comprehensive report with recommendations on how to address different limitations identified. This will include a clear list of tolls (Manual, SOP and guidelines) and systems and its status.

- CA result summary presentation in Power Point to be presented and validated in workshop with different stakeholders

Phase 2. According to phase 1 results, design or refine frameworks for effective collection of appropriate data, data integration and data use (entomological, climate, epidemiological) for peri-urban areas in Maputo city to prevent or early detect outbreaks; framework for entomological data digitalisation, integration into system defined; and framework to integrate entomological and climate data to control vectors in peri-urban areas (low transmission). Train staff on effective collection of entomological and climate data k; design appropriate training courses for entomological surveillance and data collection focused on peri-urban approaches.

Deliverables:

- Framework for entomological data collection, digitalization, analyses and integration between different sources and with epidemiological and climate data

- An effective reporting structure for data visualization and presentation of key surveillance findings to senior management for easy understanding and integration into programmatic decision-making

- Framework for malaria outbreaks planning and response

- Entomological tools and surveillance programme (SOP, Manual, guidelines) revised or developed according to the CA identified needs

Phase 3. To strengthen capacity of malaria program staff and stakeholders at central provincial and district level on entomological surveillance

Deliverables:

- Training package developed for intensive entomological course for peri-urban areas

- Training package developed for all frameworks developed and gaps according to CA results

- Training package developed for outbreak planning and response

- Malaria program staff and stakeholders trained at central provincial and district level on entomological surveillance and key developed tolls

- Budget requirements to cover an effective entomological surveillance programme.

Summary of deliverables

Table 1. Deliverables and timeline

| Phase | Products | Timeline |
| --- | --- | --- |
| One | - Inception report with the plan for CA and related tools designed and approved - Formative assessment data base with all information collected - Narrative and comprehensive report with recommendations on how to address different limitations identified. This will include a clear list of tools, approaches and methods (Manual, SOP and guidelines) and systems and its current status and shortfalls. - CA result summary presentation in Power Point to be presented and validated in workshop with different stakeholders. This PowerPoint should summarize current status of entomological surveillance, indicate Gaps and Needs, and make recommendations how to upgrade the entomological surveillance programme to enable effective malaria control programme. | 28 working days |
| Two | - Frameworks developed for entomological data collection, digitalization, analyses and integration between different sources and with epidemiological and climate data - Framework developed for malaria outbreaks plan and response - Entomological tolls (SOP, Manual, guidelines) revised or developed according to the CA identified needs - Clear, simple, easy-to-understand entomological report framework that summarizes key data and enables senior managers to easily understand and use entomological data for malaria control decision-making (in other words, develop the blank form that will be the template for future reporting) | 21 working days |
| Three | - Training package developed for intensive entomological course for effective vector surveillance in peri-urban areas - Training package developed for all frameworks developed and gaps according to CA results - Training package developed for outbreak planning and response - Malaria program staff and stakeholders trained at central provincial and district level on entomological surveillance and use of key tools and approaches - Reports on training with results from pre and post-tests, with key recommendations on how to continually build capacity | 20 working days (two weeks) |

REQUIREMENTS

Education

- Master’s or PhD in Medical Entomology

- Additional training in malaria epidemiology, vector control measures climate data in malaria surveillance context, monitoring and evaluation for malaria, including vector control interventions, is highly desirable.

Experience

- ≥10 years of experience Entomology Surveillance System. Experience in malaria Entomology is essential.

- Possess strong expertise in data integration and data use approaches (entomological, epidemiological and climate). Solid experience in climate data variables, interpretations and its integration with other health relevant components to monitor or control diseases.

- Proven experience in developing and delivering training programs in entomology, including the design of training packages for capacity building for all MISAU levels. Previous involvement in conducting evaluations of similar scope and scale is essential.

- Strong experience in programmatic malaria approaches interventions in low-transmission settings, including management of outbreaks (detect, plan and response).

Technical Skills

- Demonstrates strong oral and written communication skills in both Portuguese and English.

- Capable of managing complex inputs from multidisciplinary teams and delivering outputs within tight deadlines.

- Strong skills in research or formative assessment reports write, including the elaboration of Power Point results

- Entomological indicators interpretation

Leadership, Management, and Coordination

- The consultant works independently, consistently meets deadlines, and delivers high-quality outputs;

- They have experience collaborating with multidisciplinary teams within the Ministry of Health (MISAU), particularly with the National Malaria Control Program through entomological area, and related partner;

- Available to work on-site across all required locations, including Malaria Consortium, MISAU (NMCP and other programs), municipal health services, and health facilities;

- Actively participate in weekly and ad hoc progress review meetings to ensure effective coordination and timely delivery of results.

APPLICATION

Interested consultants should submit the following documents by 30 June 2026:

- CV highlighting relevant experience (2 pages maximum);

- A 1–2-page technical proposal outlining the approach and timeline;

- Two samples of similar work (if available), including reference of NMCP staff trained

- Financial proposal (daily rate estimated).

INTELLECTUAL PROPERTY, CONFIDENTIALITY, AND PUBLICATION RIGHTS

All data, consolidated databases, analytical code, scripts, technical reports, tables, models for malaria outbreak prevention and early detection systems, training packages developed, statistical outputs, and any other materials produced under this consultancy shall remain the exclusive property of Malaria Consortium.

The consultant hereby assigns in full to Malaria Consortium all rights over the deliverables produced under the contract, including rights of reproduction, modification, dissemination, adaptation, and use for programmatic, institutional, or scientific purposes.

The consultant commits to:

- Maintain strict confidentiality of all data and information accessed within the scope of the project and/or evaluation;

- Not use, reproduce, share, or disclose any data, code, results, or materials produced without prior, explicit, and written authorization from Malaria Consortium;

- Not undertake secondary use of the data for academic, scientific, or commercial purposes;

- Not submit manuscripts, conference abstracts, or any scientific outputs based on project/evaluation data without formal authorization from Malaria Consortium.

The consultant’s participation in any scientific publications arising from the project is not automatic and shall be subject to institutional decision by Malaria Consortium, in accordance with its internal authorship and scientific contribution policies.

Signature of the contract constitutes full acceptance of these conditions, as well as any additional specific contractual provisions.