Terms of reference

Title:  	Generating an SMC digital roadmap

Projects:  		SMC

Location of support: 	remote

Reporting to:		Poppy Farrow, Senior Digital Health Specialist

Timeframe:  	21 working days over 6 weeks starting beginning of February 2022

Rate: 	Negotiable

# Background and context

To prevent malaria in those most vulnerable to the disease’s effects in areas where transmission is seasonal, the World Health Organization (WHO) recommends seasonal malaria chemoprevention (SMC). Malaria Consortium has been a leading implementer of SMC since the WHO issued its recommendation to scale up the intervention in 2012. In 2021, our SMC programme reached 20 million children in Burkina Faso, Chad, Nigeria, Togo, Mozambique and Uganda. SMC comprises the following intervention components: planning & enumeration, procurement & supply management, community engagement, training, community-based administration of antimalarial medicines, case management & pharmacovigilance, supervision, monitoring & evaluation.

Digital tools have the potential to transform how public health interventions by increasing coverage, efficiency, quality, transparency and accountability. Though there are a range of possible use cases within the SMC intervention components, the adoption of digital tools has so far been slow. Malaria Consortium has been piloting Reveal, a geospatial intelligence platform, for use in SMC in Nigeria in 2020/21 and has some experience of the use of mobile solutions to transfer payments to SMC implementers in Chad, Nigeria and Mozambique. We also use different digital data collection platforms for a range of purposes, including coverage surveys, administrative data and research. Other SMC implementers have tested the use of different digital tools to register SMC implementers, process payments, manage supplies and collect data. However, such tools are not currently used consistently at scale. There is also a need to consider sustainability and how digital tools can be used to strengthen other mass campaigns and health systems more broadly. A strategic approach is needed to guide the definition of priorities and the use of resources, in line with Malaria Consortium’s broader digital strategy and the requirements of SMC-implementing countries.

# Details of the technical support

### Objective

This consultancy will reflect on the role Malaria Consortium’s SMC programme can play in efforts to strengthen SMC campaigns, considering future potential for supporting other mass campaigns, routine health services and health security, through increased use of digital tools. It will develop a road map that defines the longer-term vision and outlines the steps required to achieve the objectives. This will involve technical, operational and commercial considerations, including:

- Reviewing the pre-existing mapping of existing technologies and providers that support mass campaigns which has already been undertaken by the Senior Digital Health Specialist and SMC digital focal points in each country supported by Malaria Consortium.

- Building on the mapping to develop a comprehensive list of potential digital solutions, noting their capabilities, drawbacks, requirements, costs and any other relevant factors relevant to their application to the SMC intervention component.

- Synthesizing and interrogating the documented feedback received from external SMC stakeholders in our SMC countries of their digital requirements, and as necessary, supporting additional information gathering exercises.

- Documenting the requirements of internal stakeholders at organizational, programme and country level, through informational semi-structured conversations.

- Exploring scalability and sustainability in terms of country ownership, data sovereignty, offline capabilities, mobile phone ownership, innovative health worker training models including remote trainings, integration with other mass campaign digital tools and routine health system platforms and health management information systems (e.g. HMIS, DHIS2).

Key outputs

The consultant will produce a digital road map for Malaria Consortium’s SMC programme, which must include summaries of findings from desk research, internal and external consultations conducted as part of this consultancy. The road map should outline options and recommendations for consideration by the SMC programme’s leadership team in terms of the longer-term approach to increasing the use of digital tools in SMC. This should include recommendations on the following questions:

- Use of a comprehensive solution supporting multiple intervention components vs. use of a suite of separate solutions that could plug in?

- Use of a standardized solution to implement for all countries within our SMC portfolio

- Country specific tailored solutions based on internal and external stakeholder feedback and investment interests?

- What functionality do existing solutions we implement lack, that we need to develop – which could lead to the question of - Development of new solutions vs. use of existing solutions that are available?

- Use of solutions that support campaigns + routine public health interventions that drive health systems strengthening?

- Lastly, what software solutions best meet the needs of the SMC programme through the above exploration?

The road map should also include recommendations on short- and medium-term initiatives or pilot projects that may be required to achieve the longer-term objectives.

Specific activities and schedule

- Familiarisation with Malaria Consortium’s SMC portfolio and digital implementation to date, along with information gathering already conducted by the SMC workstream for the consultant to review (1 day)

- Development of semi-structured conversation guides to elicit learning and feedback from internal stakeholders (1 days)

- Engagement with 6 SMC in-country focal points through one-to-one interviews using conversation guide to collect direct feedback (4 days)

- Documenting and synthesizing internal SMC focal points’ feedback (3 days)

- Synthesis of external stakeholder feedback undertaken and captured by SMC focal points within the SMC work stream and analysis to support roadmap vision (4 days)

- Present draft SMC digital roadmap to key SMC internal experts and collate feedback (2 day)

- Revision of draft roadmap and documentation based on feedback from Malaria Consortium’s technical review process (4 days)

- Preparation and submission of final drafts of documentation (2 days)

- Final submission of SMC road map

# Payments

Malaria Consortium will make full payment on completion of all the deliverables in a single payment.

# Requirements

### Essential

- Good understanding of digital health, innovations and technological approaches to public health

- Experience of conducting similar exercises to generate and synthesise learning from a wide range of stakeholders across locations and functions

- Ability to facilitate structured discussions and derive insights and conceptualisation

- Excellent writing skills in English

- Familiarity with qualitative research techniques

- Intercultural tact and awareness

- Access to and familiarity with suitable communication platforms, preferably Microsoft Teams or Zoom

### Desirable

- Experience in digital health strategic thought leadership

- Good understanding of the epidemiology of infectious diseases in Africa

- Demonstrable experience in developing campaign-based digital health strategies

- Experience of working with stakeholders in low- and middle-income countries

- Fluency in French and or Portuguese?

# Application

Please submit your CV, proposed fee in GBP (inclusive of any tax), a recent writing sample (ideally a strategic-focused output) and two references to the point of contact below by 31st January 2022 at 17:00 GMT. In your application, please briefly state:

- How you meet the requirements outlined above

- How you propose to document the semi-structured conversations with internal stakeholders

- How you would approach the synthesis of emerging themes and recommendations

- How you would analyse the data to then support defining an overarching strategy/model/approach

The successful applicant is required to provide proof of professional indemnity insurance prior to contracting.

# Point of contact

Poppy Farrow

Malaria Consortium

The Green House, 244-254 Cambridge Heath Road, London, E2 9DA

Email: p.farrow@malariaconsortium.org